## Slide 1
Meds Counsulting LLC
National Hospital Network project charter
Overview of the business
NHN is a large integrated healthcare system serving patients across a broad hospital and outpatient network.
42 | 300+ | 11 | 2.3M
Hospitals | Outpatient sites | States | Patients per year
Problem statement
Readmissions are rising despite investment in discharge planning, care coordination, and follow-up services.
Chart: 
| 2022 | 2025
Readmission rate | 0.142 | 0.184
Annual cost exposure: more than $42M
Team roles by workstream
Workstream | Owner
Project lead and story | Can He
Data preparation and EDA | Belal Glab
Clinical risk analysis | Jingyi Cao
Predictive modeling | Santosh Kumar Chantati
Financial impact and ROI | Jeevan-Kumar Mittapalli
Care coordination operations | Adarsh Pravinbhai Patel
Dashboard and recommendations | Sam-Aquila Siddani
Stakeholders
Executive leadership and finance
Clinical and operations teams
Care coordinators and discharge planners
Patients, caregivers, and community partners
Business hypothesis
Working belief: readmissions are rising because high-risk patients are not consistently matched to the right post-discharge support.
Test focus: follow-up completion, chronic disease burden, and care coordination targeting.
Source: Option 1 Healthcare Consulting Packet and project summary
Notes: Introduce Meds Counsulting LLC and the NHN project charter. Explain NHN scale, the rising readmission problem, team workstreams, stakeholders, and the working hypothesis.

## Slide 2
Meds Counsulting LLC
Data analysis snapshot
Missing data, outliers, trends, and correlations
12,000 | 43.2% | 21.6% | 30.2%
Patients analyzed | Readmitted within 30 days | Missing follow-up status | Rows with quality flags
Data quality checks
Check | Scale | Meaning
Missing follow-up status | 2,587 rows | Care transition visibility gap
Other missing fields | 1.5-2.0% | Use cleaned/imputed file
Length-of-stay outliers | 191 rows | Review extended stays
Total care cost outliers | 72 rows | Protect ROI estimates
Negative penalty cost | 49 rows | Validate financial extract
Interpretation: data is usable, but follow-up status and financial fields need validation before final recommendations.
High-risk trend by segment
Chart: 
| 5+ chronic | Unknown follow-up | 3+ prior admit | Skilled nursing | Emergency admit
Readmission rate | 0.62339 | 0.60302 | 0.57023 | 0.54354 | 0.50881
These segments show where readmission risk concentrates before modeling.
Correlation signals
Chart: 
| Prior admits | Chronic cond. | Length of stay | Age
Correlation | 0.22 | 0.213 | 0.151 | 0.142
Prior admissions and chronic burden show the strongest early relationship with readmission.
Analytical implication
Focus the next analysis on patient risk profiles and care-transition gaps, while treating financial estimates as validation-sensitive.
Source: cleaned NHN patient, financial, and care coordination datasets; clinical segment analysis
Notes: Walk through the initial data analysis. Start with the 12,000-patient dataset and 43.2 percent readmission rate. Explain that missing follow-up status is the largest data gap, outliers affect length of stay and financial fields, high-risk segments concentrate readmissions, and correlations point toward prior admissions and chronic conditions as early risk signals.

## Slide 3
Meds Counsulting LLC
Analytical approach
Methods chosen to connect risk drivers with business decisions
Why this approach fits the NHN problem
Readmissions combine clinical risk, utilization history, discharge setting, care-transition activity, and financial exposure. The approach needs to explain drivers, group patients into action pools, and compare business value across scenarios.
Model performance evidence
Chart: 
| Accuracy | Recall | F1 score | ROC-AUC
Baseline | 0.65722 | 0.50128 | 0.5596 | 0.70712
Expanded | 0.68306 | 0.55307 | 0.60258 | 0.73965
Expanded model improves ROC-AUC to 0.74, giving a stronger basis for risk-tier decisions.
Regression analysis
Quantify risk drivers
Model readmission likelihood using clinical, utilization, discharge, and follow-up variables
Control for overlap across risk factors
Turn model output into explainable indicators
Example output: odds ratios, feature importance, predicted risk
Customer segmentation
Group patients into action pools
Create segments by chronic burden, prior admissions, discharge setting, and follow-up status
Compare readmission rates and cost exposure across segments
Prioritize care coordination for the highest-risk groups
Example output: risk tiers and intervention priority list
Market basic analysis
Place results in context
Compare NHN patterns across service lines and discharge types
Separate broad readmission pressure from segment-specific gaps
Connect trend patterns to financial scenarios
Example output: benchmark table, trend summary, ROI scenarios
Decision standard
Prioritize actions that are statistically supported, clinically explainable, operationally feasible, and financially material.
Source: NHN cleaned datasets, model metrics, and project charter analytical requirements
Notes: Explain why the approach uses three methods. Regression analysis quantifies risk drivers, customer segmentation turns the model into action groups, and market basic analysis adds operational and financial context. Point to the model evidence chart: the expanded clinical model improves ROC-AUC to about 0.74, so it is useful for risk-tier decisions, not just reporting.

## Slide 4
Meds Counsulting LLC
Business insights
Team-identified evidence and significance for leadership decisions
Readmission risk stratification
Chart: 
| D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10
Readmission rate | 0.11833 | 0.20833 | 0.2575 | 0.30333 | 0.365 | 0.4675 | 0.51833 | 0.57667 | 0.68167 | 0.82333
Risk deciles separate observed readmission rates from 11.8% in D1 to 82.3% in D10.
Business value scenario
Scenario | Reduction | Net savings | ROI
Conservative | 5.0% | $4.28M | 4.28x
Expected | 10.0% | $8.81M | 5.03x
Optimistic | 15.0% | $13.36M | 5.34x
Expected case avoids about 518 readmissions and produces $8.81M in net savings.
Team identified
Insight area | What the team found
Major performance drivers | Chronic burden, prior admissions, emergency admission, and skilled nursing discharge
Hidden opportunities | Risk tiers can focus support on patients most likely to return
Risk factors | Unknown follow-up status, high-acuity discharge, repeat utilization, and financial data quality
Unexpected findings | Unknown follow-up status has the highest observed readmission rate
Significance distinction
Lens | Meaning for NHN
Statistical | The model and deciles reliably separate higher-risk patients
Practical | Care teams can act on risk tiers before discharge or during follow-up
Business | Targeted action must improve outcomes, capacity, penalties, or savings
Board implication: prioritize insights that are credible in the model, actionable in the workflow, and material to the business case.
Source: risk score deciles, ROI scenarios, clinical segments, and cleaned NHN analysis outputs
Notes: Use this slide to explain the team's business insights. The major drivers are chronic burden, prior admissions, emergency admission, and skilled nursing discharge. Hidden opportunities come from risk-tier targeting. Risk factors include unknown follow-up status, high-acuity discharge, repeat utilization, and financial data quality. Distinguish statistical significance from practical significance and business significance. The risk-decile chart supports the statistical case, while the ROI scenario supports the business case.

## Slide 5
Meds Counsulting LLC
Recommendations
Actions, strategy, cost, benefits, timeline, and risks
$1.75M | 518 | $8.81M | 5.03x
Estimated implementation cost | Expected avoided readmissions | Expected net savings | Expected ROI
Recommendation roadmap
Action | Recommendation | Timing | Expected benefit
Short term | Pilot pre-discharge risk scoring for emergency and skilled nursing discharges | 0-3 months | Earlier targeting of highest-risk patients
Short term | Close follow-up documentation and completion gaps | 0-3 months | Lower unknown follow-up status rate
Short term | Approve dashboard KPIs and readmission reduction targets | 0-3 months | Consistent executive reporting
Long term | Expand care coordination for chronic disease and repeat-admission groups | 3-6 months | Higher intervention completion in high-risk groups
Long term | Track ROI, penalty exposure, and model performance monthly | 6-12 months | Sustained savings and model governance
Implementation timeline
Phase | Focus
0-3 months | Risk-score pilot, follow-up workflow fix, KPI governance
3-6 months | Targeted care coordination expansion and executive dashboard
6-12 months | Monthly ROI tracking and model refresh
Potential risks
Risk score adoption may stall without clear clinical workflow ownership
Follow-up documentation gaps may hide operational performance issues
ROI estimates depend on validated cost, penalty, and intervention assumptions
Cost and benefit logic
Expected scenario assumes a 10.0% readmission reduction, $1.75M implementation cost, and 518 avoided readmissions. Finance should validate assumptions before budget commitment.
Decision ask
Approve a 0-3 month pilot focused on risk scoring, follow-up visibility, and discharge review.
Source: recommendation evidence matrix, implementation roadmap, ROI scenarios, and success metrics
Notes: Present the recommended path. In the short term, pilot pre-discharge risk scoring, close follow-up documentation gaps, and align dashboard KPIs. In the longer term, expand targeted care coordination and track ROI, penalty exposure, and model performance monthly. The expected scenario estimates $1.75 million in implementation cost, 518 avoided readmissions, $8.81 million in net savings, and a 5.03x ROI. Close by naming the major risks: adoption, documentation quality, and financial assumption validation.

## Slide 6
Meds Counsulting LLC
Ethical considerations
Guardrails for fair, private, transparent, and compliant analytics
Fairness | Privacy | Governance | Compliance
Bias checks before use | Minimum necessary data | Clear ownership and audit trail | HIPAA and responsible AI review
Ethical risk areas
Issue | Concern for NHN | Required control
Algorithmic bias | Risk scores may under-serve groups if past care access was unequal | Monitor performance by age, diagnosis, discharge type, and insurance where appropriate
Customer privacy | Patient-level health and financial fields are sensitive | Use minimum necessary data and role-based access
Data governance | Missing follow-up and financial anomalies can distort decisions | Define owners, validation rules, and change logs
Transparency | Clinicians need to understand why a patient is high risk | Use explainable model outputs and plain-language score guidance
Regulatory compliance | Analytics must align with HIPAA and internal policy | Review data use, access, retention, and reporting with compliance leaders
Responsible AI | Predictions should support judgment, not replace it | Keep human review before care decisions and budget commitments
Operating principles
Principle | How to apply it
Fair | Test whether model errors differ across patient groups
Private | Limit data access to teams with a clear care or reporting need
Explainable | Show the key factors behind each high-risk flag
Accountable | Assign owners for model refresh, dashboard definitions, and issue escalation
Governance workflow
Validate data quality before model refresh or ROI reporting
Document model purpose, limitations, and approved user groups
Escalate fairness, privacy, or compliance concerns before scaling
Decision standard
Use the model as a decision-support tool only when fairness checks, privacy controls, data governance, transparency, and compliance review are in place.
Practical implication
Care teams keep final judgment over patient outreach and discharge decisions.
Source: project requirements, NHN data quality findings, risk model workflow, and healthcare compliance context
Notes: Use this slide to explain the ethical guardrails. Cover algorithmic bias, patient privacy, data governance, transparency, regulatory compliance, and responsible AI. Emphasize that the model should support human judgment rather than replace it. NHN should monitor fairness, limit access to sensitive data, validate data quality, explain score drivers, and complete compliance review before scaling.